## PM input register
# | Priority | Backlog ref | Topic / SRS | What GAPLMB must provide (deliverable) | PM Response
1 | P2 | #48 | §8.6 FR-PRT-001 — Letterhead / receipt branding | Official letterhead assets (logo, layout rules) per clarification Q48; files for pre-printed or body-only PDF use. | In the current release, all receipts, reports, and other documents will be formatted for A4 page size and made available as PDF downloads.
2 | P0 | SSO | §13.1 / §14.2 / §15.2 — SSO + MFA | IdP choice (OIDC or SAML); tenant URLs; client ID/secret or certs; redirect URIs per env; attribute mapping to app users/roles; MFA policy; UAT test users. | Access to the application is provided via username and password authentication. Once all forms within the application are submitted, accepted, approved by the client, and frozen, an additional layer of security will be implemented by enabling CAPTCHA verification.
3 | P0 | #15 | §6.1 FR-RENT-005 — TDS + GL | Signed GL rules: accounts, Dr/Cr, posting timing (invoice vs receipt vs remittance), reversals; whether marginal first-month-over-threshold TDS applies. | Which ledger accounts are used for each transaction, are menthoined Attached Excelsheet indicating the different Ledgers. posting timing (invoice vs receipt vs remittance), reversals; whether marginal first-month-over-threshold TDS applies. WILL UPDATE SEPARATELY
4 | P0 | #33 | §15.1 — Object storage / encryption | Approved cloud object store (or NIC S3-compatible); bucket/region; IAM; SSE-S3 vs KMS requirement; cutover window and approval for disk→bucket migration. | Since the client is not technically equipped to make this decision, we need to provide the most suitable solution.
5 | P0 | §8.6 DSC | FR-PRT-001 — Digital signature | Policy: class of DSC/HSM, which documents must be signed, approved CA/vendor, authorised signatories. | Digital signatures will not be implemented for signing any receipts or system-generated outputs in the current release. A placeholder may be retained to allow for potential future enhancement requests from the client. However, since this functionality is not technically required, implementing it later should not pose significant difficulty if such a requirement arises.
6 | P1 | #50 | §16.2 — Data retention | Legal/compliance stance: archive-only vs purge allowed; formal retention years per module if different from defaults; session/login retention when applicable. | System design must ensure it supports: Data Retention rules ( Should be permanent till the lifecycle of the application ) Archival or deletion policies. (As the data grows if required we can recommend archival facility at their local storage and free server space ) Audit/compliance requirements : All records to hold audit history which has been already implemented in the current system good enough.
7 | P1 | #49 | §8.3 FR-RCP-008 — Tally export | Finance UAT: import CSV/XML in Tally Prime (or agreed tool); signed list of gaps or sign-off. | WILL UPDATE SEPARATELY, The CSV format. For reports as output from out software application. Refer Attached Excelsheet indicating the different Ledgers.
8 | P1 | #17 | §6.1 FR-RENT-003 — GSTR-1 | Target filing software; sample required JSON or CA checklist; POS/state code rules beyond current export placeholders. | Keep this functionally pending for Development
9 | P2 | #16 | FR-RENT-007 — Arrears / interest GL | GL rules to post dishonour interest (heads, timing, amount basis). | If a cheque provided by a premises holder is dishonoured, the amount recorded against the tax invoice is not accounted for and a reversal entry is passed. When the user generates a new tax invoice, interest is recalculated and reflected as arrears.
10 | P2 | #31 | BR-AST-35 / BR-RCP-34 — Dishonour bank charge | Confirm auto bank-charge voucher: yes/no; default amount source; expenditure head / narrative for voucher line. | This entry would be make manually by the user.
11 | P2 | #28–30 | §8.3 FR-RCP-006 — 38 Tally heads | Process owner when live chart ≠ 38: who (DA) corrects master data; target chart approval. | Refer Attached Excelsheet indicating the different Ledgers.
12 | P2 | #39–40 | §10.1 FR-VEH — Fleet SLA | Business rules for full BR-VEH parity: calendar SLA, alerts, escalation (beyond maintenance-due + digest). | Keep this functionally as currently released in the production Enviromment. No Changes
13 | P2 | #18–19 | §5.2 / §5.5 — Allottee / Pre-receipt | Confirm flows vs SRS appendix with BA; any GAPLMB-specific exceptions in writing. | F.7 Pre-Receipt — Government / GST-Exempt Entity Rent Acknowledgement (M-02 / M-03) Issued: to Track B Government/GST-exempt entities on receipt of rent. A simple narrative acknowledgement — no GST, no itemized table, no GSTIN. Signed by Market Supervisor, [YARD NAME].