## Pending questions
Question ID | Module | Category | Question Summary | SRS Status | SRS Section Reference | SRS Resolution Note | Client Response | Responsible Officer | Response Date | Remarks
SSO | Cross-cutting | Pending policy | Government SSO / IdP (beyond email, mobile OTP, user ID + password): required for Phase 1 or deferred? | RESOLVED | §13.1 FR-USR-004; §14.2 NFR-SEC-02; §15.2 I-EXT-04 | NIC/GoG SSO is Phase 1 primary authentication (SAML 2.0 / OAuth 2.0 + OIDC). Local username/password retained as fallback (BR-USR-10–12). MFA mandatory for DA and System Admin. No client response needed.
15 | M-03 Rent / GST | Pending policy | TDS on rent: who deducts; effect on rent deposit ledger; rates, thresholds, ledger names. | RESOLVED | §6.1 FR-RENT-005; §1.5 References (S.194-I); §17.2 ASM-05 | Tenant deducts TDS under S.194-I; threshold ₹2,40,000 p.a. (configurable). TDS ledger head pre-seeded in M-05 Rent Receipt. PAN mandatory when annual rent exceeds threshold (BR-NRT-04). Design Decision #10 in §18 confirms policy.
16 | M-03 Rent / GST | Pending policy | Interest on arrears: auto-calculate? If yes, rate and rules? | RESOLVED | §6.1 FR-RENT-007 (BR-RENT-15 to BR-RENT-22) | Interest auto-calculated daily at 18% p.a. (configurable). Formula: Outstanding × Rate ÷ 365 × Days Overdue. Shown as distinct "Interest on Rent" line item on next receipt/invoice. GST applicable for Track A; exempt for Track B Govt.
17 | M-03 Rent / GST | Pending policy | GSTR-1 export: per-yard filing or consolidated for whole GAPLMB? | RESOLVED | §6.1 FR-RENT-003; §6.2 Supplier GSTIN field | Single consolidated GAPLMB GSTIN (30AAALT1317M1Z6) for whole organisation. GSTR-1 JSON export covers all yards per month (BR-RENT-07/08). Yard code used for internal tracking only — not a separate GSTIN.
18 | M-03 / SRS | Pending policy | Authoritative office/godown allottee list; sub-units mapping; Track B category codes. (Note: Non-GST flag at trader registration is already implemented.) | RESOLVED | §5.2 FR-AST-004 (BR-AST-14–16a); §5.3 Entity Classification; §8.3 FR-RCP-009 | 16 entity sub-types defined across Track A and Track B. GST Exemption Register pre-seeded with 7 Govt. entity sub-types (FR-RCP-009). GST flag set per Premises Allocation Record per sub-type (BR-AST-14–16a). Authoritative list maintained by Config Manager with DA approval.
19 | M-03 / SRS | Pending policy | Track B / pre-receipt: align invoice vs receipt document titles with SRS. | RESOLVED | §5.5.4 Pre-Receipt Record; §5.2 FR-AST-009 (BR-AST-38–42); §6.1 FR-RENT-001 | Document titles finalised: "GST Tax Invoice" for Track A; "Pre-Receipt (Demand Note)" for Track B Govt. entities. Pre-Receipt format specified at BR-AST-39; monthly auto-generation at BR-AST-38. Layouts in §19 (Appendix F).
25 | M-04 Market | Pending policy | Check post: dedicated Cashier role vs checkpoint officer only — sign-off on who issues receipts and duty-end / bank deposit reporting. | RESOLVED | §7.8 SCR-MKT-01; §8.4 FR-RCP-011–FR-RCP-014; §8.1 FR-RCP-014 | Actor at check post/counter = DO (Gate Clerk / Yard Officer) per SCR-MKT-01. Deposit workflow: DO collects → DV verifies → DA approves (FR-RCP-011–013). End-of-day Cash-in-Hand dashboard auto-emailed at 18:00 hrs (FR-RCP-014 BR-RCP-55).
28 | M-05 Receipts | Pending policy | Receipt head short codes: final sign-off (e.g. RENT, MFEE). | RESOLVED | §8.1 FR-RCP-001 (BR-RCP-01); §8.3 FR-RCP-006 Tally Ledger Master | Yard prefix codes (e.g. PF for PDN yard) assigned per GAPLMB yard/check post via M-01 Configuration Console. 38 Tally ledger heads pre-seeded from GAPLMB Tally_ledgers.xlsx at go-live. Config Manager + DA approval required for any changes.
29 | M-05 Receipts | Pending policy + confirm default | Public verification (receipt number + QR without login): allowed in production? Any conditions? (Interim: feature remains OFF until you confirm.) | RESOLVED | §8.1 FR-RCP-004 (BR-RCP-08–09); §8.2 SCR-RCP-03 Special Notes; §19 Appendix F | QR code on every receipt links to https://gaplmb.goa.gov.in/verify — verifiable without login, active in production. QR encodes: Receipt No., Amount, Date. No conditions apply.
30 | M-05 Receipts | Pending policy | Legacy ~64 receipt types mapped to six revenue heads: who signs off / authoritative mapping? | RESOLVED | §8.3 FR-RCP-006; §8.1 FR-RCP-002 (BR-RCP-04) | 38 pre-seeded Tally ledger heads from GAPLMB Tally_ledgers.xlsx are the authoritative mapping of legacy receipt types to revenue heads. Config Manager (maker) + DA (approver) sign-off required for any change. Mapping locked at go-live; additions treated as Change Requests.
31 | M-05 Receipts | Pending policy | Cheque/DD dishonour: interest formula and rent re-run rules from GAPMB (receipt reversal exists; calculation pending your formula). | RESOLVED | §5.2 BR-AST-35a–35f; §8.4 BR-RCP-34a; §8.1 FR-RCP-002 ("Dishonour of Cheque") | Fully specified: receipt marked "Not Cleared" + null/void on dishonour; ledger reversed; interest recalculated from original due date (FR-RENT-007/FR-MKT-012); manual re-invoice; bank charges mandatory, non-waivable (DA override only); "Dishonour of Cheque" Yard Receipt head is Non-GST; full audit trail (BR-AST-35f).
32 | M-06 Expenditure / Payroll | Pending policy | Salary: computed in M-01 with M-06 recording payment only, or computed in M-06? | RESOLVED | §9.1 FR-PAY-002 (BR-PAY-05); §18 Design Decision #17 | M-06 records payment only — Establishment vouchers reference payroll period but do not compute salary. No payroll computation in scope for Phase 1 (Design Decision #17).
33 | M-06 Expenditure / Payroll | Pending policy | Supporting documents: store on application server, cloud object storage (e.g. S3), or corporate DMS? | RESOLVED | §15.1 Data Tier; §14.2 NFR-SEC-07 | Scanned documents stored in secure object storage on Government-approved public cloud (AWS). Encrypted at rest using AES-256 (NFR-SEC-07). No separate corporate DMS — application object storage is the standard.
35 | M-06 Expenditure / Payroll | Pending policy | Expenditure heads: source/authority for government account code list. | RESOLVED | §9.1 FR-PAY-001 (BR-PAY-01); §1.5 References (GoG Treasury Rules, GFR 2017) | Expenditure heads pre-configured in Chart of Accounts before go-live. Authority: GoG Treasury Rules + GFR 2017 (§1.5). Configurable by System Administrator; no code change required.
36 | M-06 Expenditure / Payroll | Pending policy | Budget / limits per head per yard per year — required in system? | RESOLVED | §18 Design Decision #17; §9.1 FR-PAY-001 (BR-PAY-03) | No budget module integration required for Phase 1. Voucher amounts are NOT validated against budget heads. Budget enforcement is out of scope; to be raised as a future Change Request if needed.
39 | M-07 Fleet | Pending policy | Fuel: record per trip (pump) vs central bulk store? | RESOLVED | §10.1 FR-VEH-002 (BR-VEH-04–06) | Fuel recorded per fill-up per vehicle (odometer start/end captured per entry). Not a central bulk store. Each entry must have a linked M-06 payment voucher before finalisation (BR-VEH-06).
40 | M-07 Fleet | Pending policy | Maintenance: km-based, calendar-based, or both? | RESOLVED | §10.1 FR-VEH-006 (BR-VEH-16–19) | Both calendar-based (next service due date) AND odometer-based (next service due km) maintenance triggers are supported. 7-day advance alerts generated for both trigger types. Recurring repairs within 90 days trigger DA-level condemnation alert (BR-VEH-18).
44 | M-08 Assets / Works | Pending policy | Works / tendering: confirm internal-use-only limits until public tendering scope is decided. | RESOLVED | §11.1 FR-CNST-001 (BR-CNST-01–03) | Internal construction and works register only — records tenders, works orders, contractor details, and billing. No public e-tendering or procurement portal in scope for Phase 1. Scope confirmed via BR-CNST-01–03 and §18 design decisions.
46 | M-09 Dak | Pending policy | Scanned attachments: project storage vs organisation DMS standard? | RESOLVED | §15.1 Data Tier; §12.3 SCR-COR-01 Key Input Fields | Scanned attachments stored in the same application-level secure object storage as all other documents (§15.1 Data Tier, NFR-SEC-07 AES-256). No separate organisation DMS. Correspondence attachments: PDF max 10 MB per SCR-COR-01.
48 | M-09 Dak | Pending policy | Outward letters: who provides official print template / letterhead? | RESOLVED | §8.6 FR-PRT-001 (BR-PRT-01–07) | New §8.6 defines two print modes: (1) Plain Paper — full GAPLMB header rendered by system; (2) Pre-Printed Stationery — header suppressed, body printed to alignment. Official letterhead design, logo, and statutory content = client (GAPLMB) responsibility (BR-PRT-04). System supplies configurable template only.
49 | Cross-cutting | Pending policy | Tally export: confirm CSV column order and file path / delivery method. | RESOLVED | §8.3 FR-RCP-008 (BR-RCP-20–23) | CSV columns confirmed: Date ¦ Voucher Type ¦ Receipt No. ¦ Party Name ¦ Ledger Head ¦ Tally Group ¦ Amount (Dr) ¦ Amount (Cr) ¦ Narration. Delivery: manual download by Accounts Officer or Auditor from M-05 export screen. Both CSV and Tally XML formats supported; active format configurable by System Administrator.
50 | Cross-cutting | Pending policy | Data retention / archival: target years per record class (may depend on volume; please propose default). | RESOLVED | §16.2 Data Retention Policy | Full retention schedule defined: Employee records (Permanent); Payroll/TA/LTC (10 yr); GST Invoices (8 yr); Market Fee / Daily Arrival / Commodity records (7 yr); Receipts & Payment Vouchers (10 yr); Land Records (Permanent); Monthly Returns (Permanent); Audit Trails (5 yr); User Logs (2 yr).
52 | M-05 Receipts / UX | Pending policy | Receipt PDF: mandatory server-generated branded PDF vs browser print-to-PDF? | RESOLVED | §8.6 FR-PRT-001 (BR-PRT-02); §8.1 FR-RCP-004 (BR-RCP-08–09) | Mandatory server-generated PDF for all receipts — includes full header, logo, QR code, and digital signature of issuing officer (BR-RCP-08). Browser print-to-PDF is NOT the method. Print Mode selector (§8.6) controls header visibility but PDF is always server-generated.
42 | M-08 AMC | Confirm for production (interim in system) | AMC bills: monthly auto-generation via scheduled job acceptable for production? Quarterly/Annual remain manual until you confirm. | RESOLVED | §11.1 FR-CNST-003 (BR-AMC-04); §11.2 SCR-CNST-03 | All AMC billing cycles (Monthly, Quarterly, Annual) are MANUAL. No scheduled batch job or auto-generation is implemented (BR-AMC-04). [Generate AMC Invoice] is a manual trigger on SCR-CNST-03. Automation explicitly out of scope unless approved as future Change Request.
45 | M-09 Dak | Confirm for production (interim in system) | Dak inward diary numbering: confirm per_yard vs central (single HO sequence) for production. | RESOLVED | §12.1 FR-COR-001 (BR-COR-01); §12.3 SCR-COR-01 | Per-yard (per-location) numbering confirmed: IN-[LOC]-[YYYY]-[NNNNN] for inward; OUT-[LOC]-[YYYY]-[NNNNN] for outward (BR-COR-01). HO and each Sub-Yard maintain independent sequences. No central single HO sequence.
51 | Integration | Confirm for production (interim in system) | Payment gateway webhooks: confirm HMAC/signature policy vs other callback security. | OPEN | §15.2 I-EXT-03; §8.1 FR-RCP-003 (BR-RCP-06) | SRS confirms HTTPS for payment gateway and 10-min callback timeout with auto-reconciliation (BR-RCP-06). However, specific HMAC / digital-signature policy for incoming webhook callbacks is NOT specified. Client must confirm: (a) HMAC-SHA256 shared secret, (b) IP whitelist only, or (c) gateway-provided signature header — before M-05 gateway integration is finalised.
53 | Ops / Audit | Confirm for production (interim in system) | Batch/cron audit log actor: use literal system user vs real users.id for compliance (AUDIT_SYSTEM_USER_ID). | OPEN | §14.2 NFR-SEC-05; §3.2 BR-WF-06 | Audit trail is immutable and logs actor + timestamp + IP for all workflow transitions (NFR-SEC-05, BR-WF-06). However, SRS does not define whether scheduled batch/cron jobs log under a reserved AUDIT_SYSTEM_USER_ID or under a real user ID. Client must confirm preferred approach for compliance with GoG audit requirements.
Total Questions | 27
Resolved by SRS | 25
Remaining OPEN | 2

## Instructions
GAPLMB IOMS — pending clarifications for client response
How to use this workbook
1. Open the sheet "Pending questions".
2. Fill columns E–H: Client response, Responsible officer, Response date, Remarks.
3. Return the completed file to the project coordinator.
Category meanings
Pending policy | No final answer yet; your written response drives design or go-live policy.
Pending policy + confirm default | Policy decision needed; software may already use a safe default until you confirm.
Confirm for production (interim in system) | A working default exists for UAT; please confirm or override for production.
Reference | Internal: docs/CLIENT-CLARIFICATION-PENDING.md and docs/CLIENT-CLARIFICATION-RESPONSES-2026.md

## Legend
Colour | Status | Meaning
| RESOLVED | The SRS v3.0 already contains a full policy or design decision that addresses this clarification. No further client response is required for development to proceed.
| OPEN | The SRS does not yet specify this policy. A written client response is still required before the affected module can be finalised for production.