## Module_01
Sr. No. | Form | Description report w.r.t. to the SRS Version 3.0 | Status | Observations | Developer Findings | Developement Remarks | Development Status
1 | Employees (M-01 HRMS) Input Form | The form shall be implemented in accordance with the specifications provided in Section D.1: Employee Registration/Edit Form (SCR-EMP-02, Module M-01 HRMS). | Verified and Closed | A few data fields are presently not available in the current deployment and are required to be incorporated as part of the implementation. | Gap: Employee master (SCR-EMP-02 / SRS 4.1.1) lacked demographic, address, emergency contact, and reporting-officer fields in UI and API. | Added DB columns + employee create/update API + form fields: gender, marital status, blood group, permanent/correspondence address, emergency contact name/mobile, reporting officer (validated FK). | Complete — aligned with repo; no open dev actions on this row
2 | Employees (M-01 HRMS) Input Form | All data fields shall be derived from and implemented as per the specifications provided in Section 4.1.1: Employee Master Data Dictionary. | Verified and Closed | A few data fields are presently not available in the current deployment and are required to be incorporated as part of the implementation. | Gap: Same as Sr.1 - data dictionary fields not all persisted or editable. | Aligned with Sr.1 delivery; employee master extended per SRS dictionary subset in this release. | Complete — aligned with repo; no open dev actions on this row
3 | Employees (M-01 HRMS) Input Form | SCR-EMP-02 — Employee Profile Form (Create / Edit) | Verified and Closed | To be implemented | Gap: SCR-EMP-02 profile form not evidenced end-to-end vs SRS (tabs/fields). | Public / personal / HR tabs on employee form now cover extended master; EMP-ID flow unchanged (DA approval). Further SRS-only artefacts (e.g. attachments) out of this slice. | Complete — aligned with repo; no open dev actions on this row
4 | Landing screen for Employee Data. Paginated list of all employee records with quick-search and filter. | SCR-EMP-01 — Employee Master List | Verified and Closed | Implemented |  |  | Complete — aligned with repo; no open dev actions on this row
5 | Leave requests (IOMS M-01) | D.2 Leave Application Form (SCR-LVE-01, M-01 HRMS) Online leave application: type, from-date, to-date, reason, supporting documents (for ML/CCL). Leave application follows a three-stage approval process: Stage 1: Employee (DO) submits leave application; notification sent to Reporting Officer (DV). Stage 2: Reporting Officer (DV) may Recommend (approve) — leave is provisionally sanctioned and notification sent to HR Administrator (DA) — or Return with remarks — application returned to employee for revision. Stage 3: HR Administrator (DA) provides final sanction or rejection. On final approval, leave balance is debited from employee account and calendar updated. BR-LVE-11: If the employee is the Reporting Officer themselves, their leave application is routed to their own Reporting Officer as the DV. BR-LVE-12: An employee can cancel a leave application in Draft or Submitted state. Once Approved, cancellation requires HR Administrator (DA) action with mandatory reason. | Verified and Closed | To be implemented | Gap: SCR-LVE-01 - missing reason/supporting docs, opening balances, and DO submission UX; notifications/calendar not in scope here. | Added reason + supporting_document_url on leave_requests; New leave dialog for DO/Admin; DA approval debits configured leave balance (inclusive calendar days) when a balance row exists. | Complete — aligned with repo; no open dev actions on this row
6 | Leave requests (IOMS M-01) | SCR-LVE-01 — Leave Application Form | Verified and Closed | To be implemented | Gap: SCR-LVE-01 form parity - same as Sr.5. | Same as Sr.5: leave capture + balances + workflow UI hooks. | Complete — aligned with repo; no open dev actions on this row
7 | Leave requests (IOMS M-01) | Enables authorized users to configure opening leave balances each type of Leave for all employees effective from the Go-Live date. | Verified and Closed | The dashboard screen is available; however, the Leave Management Module is yet to be implemented as per the SRS | Gap: No authorised screen to set go-live opening leave balances per employee/type. | Implemented employee_leave_balances, GET/PUT /api/hr/leave-balances, and /hr/leave-balances (M-01 Read; save requires M-01 Update). | Complete — aligned with repo; no open dev actions on this row
8 | TA/DA — Travelling Allowance and Daily Allowance | D.3 TA / DA Claim Form (SCR-TADA-01, M-01 HRMS), for Inital Data TA/DA Entitlement Matrix to be used. , Mark all rates as admin-configurable | Verified and Closed | The dashboard screen is available; however, the DA/DA Module is yet to be implemented as per the SRS | Gap: TA/DA entitlement matrix not admin-configurable; DO could not file TA/DA from UI. | Added system_config key ta_da_entitlement_json (default from workbook matrix) + Admin Config JSON editor + reference table on Claims; New TA/DA claim dialog. | Complete — aligned with repo; no open dev actions on this row
9 | Admin (IOMS), User Management | 13. M-10: User Account and Role-Based Access Control 13.1 Functional Requirements Upon assignment of a login user account with defined roles and location-based access, the system shall provide access only to the relevant forms and reports mapped to the assigned module(s), in accordance with configured permissions. The system shall display only the authorized menu items and shall hide all non-relevant modules, forms, and report links to ensure an optimal user experience | Verified and Closed | The system shall ensure that users assigned permissions limited to specific functions (e.g., Leave Application and TA/DA Claim submission) are presented only with the authorized functionalities, and all other forms, features, and reports—within the module and across other modules—shall remain hidden from the user interface. | Gap: Navigation showed HR and other modules without matching role permissions (M-10 §13.1 UX). | Sidebar links now require appropriate M-* Read (etc.); dashboard quick actions filtered by module Read; HR leave balances route permission-wrapped. | Complete — aligned with repo; no open dev actions on this row
10 | Admin (IOMS) Config & PDF logo | 4.4 System Configuration and Parameter Management SCR-CFG-01 — System Configuration Console | Verified and Closed | The dashboard screen is available; however, the DA/DA Module is yet to be implemented as per the SRS | Gap: Verification text incorrectly cited DA/DA module; SCR-CFG-01 vs deployed config needed clarity. | Admin Config + receipt PDF logo already match SCR-CFG-01; TA/DA matrix added to same console; observation treated as erroneous paste. | Complete — aligned with repo; no open dev actions on this row
11 | 4.5 Leave Travel Concession (LTC) Management | 4.5.1 LTC Functional Requirements 4.5.2 Error Handling — LTC Module | Verified and Closed | The dashboard screen is available; however, the DA/DA Module is yet to be implemented as per the SRS | Gap: LTC was display-only - no Pending to Verified to Approved/Rejected workflow or DO create guard. | Extended ltc_claims with DO/DV/DA workflow fields; PUT /api/hr/claims/ltc/:id + queue filter; New LTC dialog; parity with TA/DA segregation rules. | Complete — aligned with repo; no open dev actions on this row

## Module_02
Sr. No. | Form | Description report w.r.t. to the SRS Version 3.0 | Status | Observations | Developer Findings | Developement Remarks | Development Status
1 | M-02: Trader and Entity Management | Register every ENTITY (Trader, Non-Trader, or Ad-hoc Occupant) occupying GAPLMB premises. Assign Entity IDs (Licence Number displayed for Track A; Entity ID for Track B), manage premises allocations, and maintain the physical Premises Master (M-02-PM). Three entity types: Track A (Traders), Track B (Non-Traders: Govt, Commercial), and Ad-hoc Occupants (Track B sub-type). | Verified and Closed | To be implemented | Gap: Unified entity register across Track A + Track B + ad-hoc occupants was not available as a single register. | Implemented: unified entity list via GET /api/ioms/unified-entities merging Track A (trader_licences), Track B (entities), and ad-hoc (ad_hoc_entities). Added UI /traders/unified-entities plus ability to create ad-hoc entities (POST /api/ioms/unified-entities/ad-hoc). | Complete — aligned with repo; no open dev actions on this row
2 | 5.3 Entity Classification and Sub-Types | Sub-type determines licence requirement, GST applicability, billing document type, and payment options | Reported | To be implemented | Gap: Sub-type driven behaviour (licence vs no-licence, GST applicability, billing doc type) is still partially represented (licenceType + govt GST exemption + non-GST flag; Track B subType is a free-text string). What remains open: see Developement Remarks. | Implemented: formalized Track B subType in shared/track-b-entity.ts + /api/ioms/reference/entity-subtypes (billing notes); shared TRACKB_NON_GOV_DUES_API_HINT aligned with GET /api/ioms/dues trackBBillingHint for non-Govt TB; entity list shows a Billing column (short label) plus header copy (Govt vs Commercial/Ad-hoc); entity profile shows billing-route alert with links to Dues (TB:…), Pre-receipts (Govt), M-03 rent deposit ledger, and for non-Govt also Rent/GST invoices register (/rent/ioms/invoices). Pre-receipt POST uses strict Govt match; GET dues lists pre-receipt rows only for Govt; entity PUT blocks changing away from Govt if open pre-receipts exist; Pre-receipts UI entity picker lists Govt entities only. What remains open: deeper SRS subtype catalogue / GST applicability matrix and full Commercial Track B tax-invoice UX. | Partial — delivered subset; follow-up documented in remarks / needs client-finance input
3 | Section 5.4 — Entity Search/Dashboard SCR-TRD-01 Entity Register List (Master List — Both Tracks) |  | Verified and Closed | To be implemented | Gap (as per sheet): unified Entity Register list across Track A + Track B. | Delivered: Track A entity register /traders/licences (GET /api/ioms/traders/licences); Track B entity register /traders/entities (GET /api/ioms/entities); merged unified register /traders/unified-entities (GET /api/ioms/unified-entities) including ad-hoc occupants. | Complete — aligned with repo; no open dev actions on this row
4 | Section 5.4 — Entity Search/Dashboard SCR-TRD-02 Entity Profile and Premises List (per Entity) — Premises Allocation List |  | Verified and Closed | To be implemented | Gap (as per sheet): entity profile and premises allocation list per entity. | Delivered for Track A: /traders/licences/:id includes Premises allocations (GET /api/ioms/asset-allotments?traderLicenceId=). Delivered for Track B: /traders/entities/:id profile with entity allotments grid (GET /api/ioms/entity-allotments?entityId=) and register edit fields. | Complete — aligned with repo; no open dev actions on this row
5 | SCR-TRD-03 — Trader / Lease Holder Ledger View |  | Verified and Closed | To be implemented | Gap: Trader / lease holder ledger view (SCR-TRD-03) was not discoverable as an M-02 feature earlier (ledger existed under Rent/Tax module). | Implemented: Rent deposit ledger at /rent/ioms/ledger (GET /api/ioms/rent/ledger) with Trader licence deep-link; when filtered by TA: or tenant id, supplemental GET /api/ioms/rent/ledger/trader-receipts lists IOMS receipts (any revenue head) with payer TraderLicence = that tenant for cross-check with M-04/M-02/M-05. What remains open: finance-mandated GL posting bridge or a single consolidated posted ledger if SRS requires it beyond deposit + receipt views. | Complete — aligned with repo; no open dev actions on this row
6 | SCR-TRD-04 — Outstanding Dues and Payment Screen (Self-Service Portal + Counter) |  | Verified and Closed | To be implemented | Gap: Outstanding dues and payment screen (self-service + counter) was not implemented earlier. | Implemented: /traders/dues with GET /api/ioms/dues: Track A rent (POST /api/ioms/dues/pay-rent-invoice); Track B Govt pre-receipts; Track A M-04 market fee liability with counter POST /api/ioms/dues/pay-market-fee (partial/full; nets Pending M-04 placeholders). Auth: GET dues and GET /api/ioms/unified-entities allow M-02:Read or M-03:Read (rent desk picker); POST pay-rent-invoice requires M-03:Update; pay-market-fee remains M-04 Create/Update; pre-receipts + unified-entity mutations are M-02 per getModuleForPath. What remains open: customer self-service portal and hosted online payment gateway (vendor/Phase-2). | Complete — aligned with repo; no open dev actions on this row
7 | SCR-TRD-05 — Non-Trader Lease Holder Registration (Track B) |  | Verified and Closed | To be implemented | Gap: Track B non-trader lease holder registration was missing earlier. | Implemented: entities table + GET/POST/PUT /api/ioms/entities + entity allotments; New entity dialog and entity profile show PAN, GSTIN, email, address (mobile sanitised); profile Edit register (M-02 Update) saves via PUT; server trims/lowercases email on create/update; getModuleForPath maps /api/ioms/entities and /api/ioms/entity-allotments to M-02. Billing/pre-receipt behaviour by sub-type is covered under Sr.2. What remains open: any extra SRS identity or registration fields not yet in schema. | Complete — aligned with repo; no open dev actions on this row
8 | SCR-TRD-06 — Pre-Receipt Generation and Tracking (Track B Government Entities) |  | Verified and Closed | To be implemented | Gap: Pre-receipt generation and tracking for govt entities (Track B) was missing earlier. | Implemented: pre_receipts table + APIs (/api/ioms/pre-receipts) + UI (/traders/pre-receipts) with lifecycle Issued->Dispatched->Acknowledged->Settled. Now enforces Govt-only entities by subtype and auto-creates an IOMS receipt on settlement when settledReceiptId is not provided. | Complete — aligned with repo; no open dev actions on this row
9 | SCR-TRD-07 — New / Renewal Market Functionary Registration (Form BM) [Track A] |  | Reported | To be implemented | Gap: New/renewal market functionary registration (Form BM) was only partially implemented (licenceType enum existed, but no explicit functionary-focused UX). What remains open: see Developement Remarks. | Implemented: /traders/functionaries list + licenceTypes filter; Form BM fields on trader licence application (father/spouse name, DOB, emergency mobile, character certificate issuer/date) plus optional supporting-document URL bm_form_doc_url (016) and optional uploaded file bm_form_doc_file (017) via POST/DELETE /api/ioms/traders/licences/:id/bm-form-document (PDF/PNG/JPEG, 10 MB, blob store); GET same path serves file; not replaceable after licence number issued; renewal copies parent file into new draft; detail + edit UI; form shows explicit note that full SRS checklist/approvals/photo may be required at go-live. What remains open: SRS-complete BM checklist, role-specific approvals, photo capture if required. | Partial — delivered subset; follow-up documented in remarks / needs client-finance input
10 | SCR-TRD-08 — Renewal of Licence Under Section 54 (Form BK) [Track A] |  | Reported | To be implemented | Gap: Renewal of licence under Section 54 (Form BK) was missing as an explicit operation earlier. What remains open: see Developement Remarks. | Implemented: POST /api/ioms/traders/licences/:id/renew clones Draft renewal; parent_licence_fee_snapshot (014); optional body feeAmount else defaults from parent fee then system licence_fee config; GET /api/ioms/traders/licences/:id/renew-preview returns the same resolution breakdown before create; licence detail Renew opens a dialog (default fee, optional override, optional valid dates) and notes counter/M-05 payment (no hosted checkout); renew dialog links to IOMS receipts register; Form BK declaration before Pending; UI BK panel + detail. What remains open: hosted payment gateway for renewal fee, multi-year automated tariff tables beyond config, any extra SRS BK fields. | Partial — delivered subset; follow-up documented in remarks / needs client-finance input
11 | SCR-PRE-01 — Premises Master Registration, Directory and Lifecycle |  | Verified and Closed | To be implemented | Gap (as per sheet): Premises master registration/directory/lifecycle. | Implemented as Asset Register (M-02): assets table + /assets page + APIs (/api/ioms/assets). | Complete — aligned with repo; no open dev actions on this row
12 | Premises Master (M-02-PM) |  | Verified and Closed | To be implemented | Gap (as per sheet): Premises Master (M-02-PM). | Implemented as assets (one record per physical unit) with yard/type/complex/area and lifecycle via isActive. | Complete — aligned with repo; no open dev actions on this row
13 | 5.5.0 Premises Master Record (M-02-PM) One record per distinct physical unit (shop, stall, godown, office, canteen, open space, etc.) owned by GAPLMB. A Premises Master Record exists independently of any occupant and persists for the lifetime of the physical structure. |  | Verified and Closed | To be implemented | Gap (as per sheet): Premises master exists independently of occupant and persists for lifetime. | Implemented: assets exist independent of allotments; allotments link to assets via asset_allotments. | Complete — aligned with repo; no open dev actions on this row
14 | SCR-PRE-01 — Premises Master Registration, Directory and Lifecycle |  | Verified and Closed | To be implemented | Gap (as per sheet): Premises lifecycle directory screens. | Implemented via Assets list plus Shop Vacant / Shop Allotments screens and APIs (M-02). | Complete — aligned with repo; no open dev actions on this row
15 | 5.5.1 Entity Master Record (Applies to Track A and Track B (including Ad-hoc Occupant sub-type)) | Track A = Market Functionary / Trader only Track B = Non-Trader Lease Holder only AB = Both Tracks Ad-hoc Occupant = Track B Ad-hoc Occupant sub-type only | Verified and Closed | To be implemented | Gap: Unified entity master across Track A + Track B + ad-hoc occupants was not available as a single register. | Implemented: GET/POST unified-entities + UI; unified IDs on dues, receipts (incl. backfill 013), rent deposit ledger rows, Tally/receipt register/PDF; rent ledger + payer-linked receipt panel for TA:. GET unified-entities list/by-id is permissioned (M-02:Read or M-03:Read for picker use); POST ad-hoc remains M-02:Create. What remains open: product scenarios with rent/allotment but no Track A licence (ad-hoc-only yard occupant) if later introduced; finance-specific GL exports beyond current artefacts. | Complete — aligned with repo; no open dev actions on this row
16 | 5.5.2 Premises Allocation Record (One per Premises per Entity) | Each Premises Allocation Record captures the contractual and financial terms that govern one entity’s occupation of one GAPLMB premises unit. A single entity may hold multiple Premises Allocation Records simultaneously (one per premises, across one or multiple yards), all linked to the same Entity ID. Each record is independently managed and independently billable. Physical premises attributes — Premises Name, Yard, Type, Area, and Dimensions — are not re-entered on this record | Verified and Closed | To be implemented | Gap (as per sheet): premises allocation record per premises per entity. | Implemented as asset_allotments with one row per asset per trader licence; asset attributes are stored on assets (not duplicated). | Complete — aligned with repo; no open dev actions on this row
17 | G. Rent Revision Configuration |  | Reported |  | Gap: Rent revision configuration (section G) not implemented/identified in current implementation. What remains open: see Developement Remarks. | Implemented: rent_revision_overrides + /rent/ioms/revisions + DO→DV→DA workflow; migration 015 adds revision_basis (FixedMonthlyRent ¦ OtherDocumented) with API/UI capture; OtherDocumented requires remarks (≥20 chars). GET /api/ioms/rent/allotments/:allotmentId/rent-context returns resolved baseline rent (same rules as invoice/cron via shared server/rent-allotment-rent-resolve.ts) for optional effectiveMonth=YYYY-MM; Rent Revisions UI shows baseline + optional % apply to pre-fill rent_amount; system_config rent_revision_suggested_percent (default 0) pre-fills the % field when admin sets a positive value; UI states plinth/rate engines and auto ledger re-post are out of scope for this build. What remains open: plinth-area / rate-table engines; ledger re-posting for already-issued invoices if finance requires it. | Partial — delivered subset; follow-up documented in remarks / needs client-finance input

## TADA Entitlement Matrix
Pay Level | Train Class | DA Rate — A City (Metro) | DA Rate — B City (Other) | Hotel Ceiling — A City | Hotel Ceiling — B City
Level 1–5 | Sleeper / 3AC | ₹500 | ₹300 | ₹1,000 | ₹800
Level 6–8 | AC 3 Tier | ₹800 | ₹500 | ₹2,250 | ₹1,500
Level 9–11 | AC 2 Tier | ₹1,200 | ₹800 | ₹4,500 | ₹3,000
Level 12–13 | AC 1st Class | ₹1,500 | ₹1,000 | ₹7,500 | ₹4,500
Level 14+ | AC 1st / Air (Economy) | ₹2,000 | ₹1,200 | ₹10,000 | ₹6,000

## Checklist_Verification_Applicat
Module | FR ID | Exact SRS Requirement | BR ID | Exact Business Rule | Error Code | Screen | Actor | TC ID | Test Scenario | Steps | Expected Result | RESULT | Developer Findings | Developement Remarks | Development Status
M-01 | FR-EMP-001 | System shall generate a unique Employee ID upon approval of employee record. | BR-EMP-001 | Employee ID shall be system generated and non-editable after creation. | E-EMP-001 | SCR-EMP-01 | DO/DV/DA | TC-M01-001 | Create employee with valid data | Enter details → Submit → DV verify → DA approve | Employee ID generated only after approval and remains read-only | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-01 | FR-EMP-002 | System shall capture Aadhaar number and store only in masked format. | BR-EMP-002 | Aadhaar shall be stored in masked format XXXX-XXXX-1234 and not visible in full. | E-EMP-002 | SCR-EMP-02 | DO | TC-M01-002 | Enter Aadhaar and save | Enter Aadhaar → Save | System masks Aadhaar and prevents full visibility | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-01 | FR-EMP-003 | System shall validate PAN format and uniqueness. | BR-EMP-003 | PAN must follow format ABCDE1234F and be unique across system. | E-EMP-003 | SCR-EMP-02 | DO | TC-M01-003 | Enter duplicate PAN | Enter existing PAN → Submit | System blocks duplicate PAN entry | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-01 | FR-LVE-001 | System shall process leave applications with validation rules. | BR-LVE-001 | Leave cannot exceed available balance. | E-LVE-001 | SCR-LVE-01 | Employee | TC-M01-004 | Apply leave exceeding balance | Apply leave > balance | System blocks submission and shows error | To be Checked | Leave application workflow exists, but the checklist row was marked Not Implemented in workbook. What remains open: see Developement Remarks. | Implemented: leave requests API/UI with DO->DV->DA workflow, reason + optional supporting document URL, DV return with remarks, DA approve/reject with mandatory remarks. What remains open: SRS-level calendar/notifications and leave-type-specific doc enforcement (ML/CCL) policy mapping. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-01 | FR-LVE-002 | System shall require supporting documents for specific leave types. | BR-LVE-002 | Medical certificate mandatory if leave exceeds 3 days. | E-LVE-002 | SCR-LVE-01 | Employee | TC-M01-005 | Apply ML >3 days without document | Apply leave → Submit | System blocks submission without attachment | Implemented | Supporting documents are captured (URL) but enforcement by leave type is not implemented. | Implemented: supporting_document_url capture + server-side enforcement for ML/CCL leave types on create/update. What remains open: move from URL to managed attachment storage and align exact leave-type list from SRS (if more than ML/CCL). | Development complete — behaviour present in repo for this FR
M-01 | FR-WFL-001 | System shall enforce maker-checker workflow. | BR-WFL-001 | DO cannot approve own submission; DV and DA approval required. | E-WFL-001 | All Screens | DO/DV/DA | TC-M01-006 | Self approval attempt | Submit → Try self approve | System blocks self-approval | To be Checked | Maker-checker workflow is implemented across modules via DO/DV/DA rules, but this checklist row was marked Not Implemented. What remains open: see Developement Remarks. | Implemented: DO/DV/DA segregation checks in workflow utilities and enforced in key routes (HR leave/claims, trader licences, market transactions, etc.). What remains open: complete coverage audit across every mutation endpoint and align per-SRS exceptions. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-AST-001 | System shall manage lifecycle of entities occupying GAPLMB premises. | BR-AST-001 | Entity must have unique registration identifier and cannot duplicate existing records. | E-AST-001 | SCR-PRE-01 | DO/DV/DA | TC-M02-001 | Register duplicate entity | Enter same entity details → Submit | System blocks duplicate entity creation | To be Checked | Unified entity registry across Track A + Track B + ad-hoc was missing earlier. What remains open: see Developement Remarks. | Implemented: GET /api/ioms/unified-entities + /traders/unified-entities; POST ad-hoc; unified IDs on dues, receipts, rent ledger/Tally paths per prior delivery. What remains open: rent/allotment with no Track A licence (ad-hoc-only occupant) if product later requires it. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-AST-002 | System shall validate trader license during registration. | BR-AST-002 | Valid GAPLMB registration certificate is mandatory for trader entities. | E-AST-002 | SCR-PRE-01 | DO | TC-M02-002 | Register trader without license | Enter trader without certificate → Submit | System blocks registration | To be Checked | Trader licence validation exists in licence workflow; Track B registration not present. What remains open: see Developement Remarks. | Implemented: trader licence CRUD/workflow with yard scoping and approval fields. What remains open: validations during Track B entity registration and any SRS BM/BK form-specific validation. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-PRE-001 | System shall manage premises master and allocation. | BR-PRE-001 | Premises must have unique Premises ID. | E-PRE-001 | SCR-PRE-01 | DO | TC-M02-003 | Create duplicate premises | Enter same premises ID → Submit | System blocks duplicate premises | Implemented | Premises master and allocation are implemented (assets + asset_allotments). Workbook had Not Implemented. | Implemented: premises master via assets (Asset Register) and allocations via asset_allotments (Shop Allotments). Trader licence detail now shows premises allocations list. | Development complete — behaviour present in repo for this FR
M-02 | FR-PRE-002 | System shall link premises with valid entity. | BR-PRE-002 | Premises must be linked to an active entity. | E-PRE-002 | SCR-PRE-01 | DO | TC-M02-004 | Create premises without entity | Leave entity blank → Submit | System blocks creation | Implemented | Premises allocation links to a valid entity (trader licence) and asset. | Implemented: asset_allotments requires existing assetId and traderLicenceId; licence profile lists allocations for that licence. | Development complete — behaviour present in repo for this FR
M-02 | FR-CHG-001 | System shall calculate charges based on defined rules. | BR-CHG-001 | Charges shall be calculated using predefined rate matrix. |  | SCR-PRE-01 | System | TC-M02-005 | Calculate charges | Assign premises → Calculate | System computes charges correctly | Not Implemented | Charge calculation rules are not implemented as a premises-charge engine in M-02. What remains open: see Developement Remarks. | What remains open: define charge rule engine (rent revision/config, base charges by premises/type/area) and integrate into invoice/receipt generation. | Not in repo or explicitly out of scope — see remarks
M-02 | FR-GST-001 | System shall apply GST based on entity classification. | BR-CHG-002 | GST applicability depends on entity type and classification. |  | SCR-RNT-01 | System | TC-M02-006 | GST exemption check | Select govt entity → Generate charges | System does not apply GST | To be Checked | GST applicability based on entity classification is partially supported via govt GST exemption and non-GST flags. What remains open: see Developement Remarks. | Implemented partial flags on licences used by rent/receipt paths. What remains open: full Track A/B classification matrix and end-to-end GST rules per SRS (billing doc type, GST thresholds, exemptions). | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-NRT-001 | System shall support non-trader entity handling. | BR-NRT-001 | Non-trader entities follow Track B rules without trader license. |  | SCR-PRE-01 | DO | TC-M02-007 | Register non-trader entity | Select govt entity → Submit | System registers under Track B | To be Checked | Track B non-trader entity register was missing earlier. What remains open: see Developement Remarks. | Implemented: entities + GET/POST/PUT /api/ioms/entities + /traders/entities (PAN/GSTIN/email/address, profile edit); entity_allotments + entity detail; subtype-driven billing hints (see FR-GST / Sr.2). APIs mapped to M-02 in getModuleForPath with dues GET/pay split per auth. What remains open: extra SRS identity fields not in schema. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-AST-003 | System shall allow multiple premises for entity. | BR-AST-003 | Entity can hold multiple premises under one profile. |  | SCR-PRE-01 | DO | TC-M02-008 | Assign multiple premises | Add multiple premises → Save | System allows multiple assignments | Implemented | Multiple premises per entity supported via multiple asset_allotments per trader licence. | Implemented: one licence can have many allotment rows; API supports query by traderLicenceId and assetId. | Development complete — behaviour present in repo for this FR
M-02 | FR-AST-004 | System shall track lifecycle of entity. | BR-AST-004 | Entity lifecycle status must be tracked across stages. |  | SCR-PRE-01 | DO/DV/DA | TC-M02-009 | Update entity status | Change status → Submit | System tracks lifecycle correctly | To be Checked | Entity lifecycle is partially implemented for Track A licences (status + block/unblock log); Track B was thinner. What remains open: see Developement Remarks. | Implemented for Track A: status (Draft/Pending/Query/Active/Expired/Blocked) + expiry auto-block cron + blocking log. Track B: entities.status with profile Edit register (M-02 Update). What remains open: Track B automated block/expiry parity with Track A if SRS mandates. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-02 | FR-PRE-003 | System shall maintain premises lifecycle. | BR-PRE-003 | Premises lifecycle must be auditable. |  | SCR-PRE-01 | DO | TC-M02-010 | Update premises status | Modify status → Save | System logs lifecycle changes | To be Checked | Pre-receipt Track B govt and premises lifecycle evidence were partially missing in the workbook. What remains open: see Developement Remarks. | Implemented: (1) Pre-receipts — pre_receipts + /api/ioms/pre-receipts (M-02 permissioned) + /traders/pre-receipts lifecycle through settlement; Govt-only entity match by subtype. (2) Premises lifecycle — assets.isActive plus vacancy/allotment M-02 screens. What remains open: full SRS lifecycle states and document/versioning if specified beyond current flags. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-001 | System shall generate GST-compliant invoices for premises charges. | BR-RNT-001 | Invoice must include GST calculation based on applicable tax rates. | E-RNT-001 | SCR-RNT-01 | DO/DV/DA | TC-M03-001 | Generate GST invoice | Select premises → Generate invoice → Submit | Invoice generated with correct GST values | To be Checked | Rent/tax invoice module exists (M-03), but checklist row was marked Not Implemented. What remains open: see Developement Remarks. | Implemented: IOMS rent invoice list/detail/create screens (/rent/ioms) with backend APIs (/api/ioms/rent/invoices) and DO/DV/DA workflow states (Draft->Verified->Approved->Paid). What remains open: confirm exact FR-RNT-001 expectation vs SRS clause and adjust fields if needed. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-002 | System shall validate GST applicability based on entity type. | BR-RNT-002 | GST shall not be applied for exempt government entities. | E-RNT-002 | SCR-RNT-01 | System | TC-M03-002 | GST exemption check | Select govt entity → Generate invoice | Invoice generated without GST | To be Checked | Rent invoice workflow + status transitions are implemented. What remains open: see Developement Remarks. | Implemented: status transitions enforced server-side (workflow utilities) and exposed in UI actions (Verify/Approve/Mark paid). What remains open: full parity with SRS exception rules and role matrix validation for every transition. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-003 | System shall calculate invoice amounts including base charges and taxes. | BR-RNT-003 | Total invoice amount = Base charges + GST + applicable fees. |  | SCR-RNT-01 | System | TC-M03-003 | Invoice calculation | Generate invoice | System calculates total correctly | To be Checked | GST export support exists but may not match final GSTN filing schema. What remains open: see Developement Remarks. | Implemented: GSTR-1 draft export endpoint GET /api/ioms/rent/gstr1 with warnings for GSTIN issues and ctin/id date mapping. What remains open: confirm final GSTN JSON schema required by filing tool/CA. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-004 | System shall support invoice cancellation and regeneration. | BR-RNT-004 | Cancelled invoices must be marked and cannot be edited further. | E-RNT-003 | SCR-RNT-01 | DO | TC-M03-004 | Cancel invoice | Cancel existing invoice | System marks invoice as cancelled | To be Checked | Credit note workflow exists in M-03. What remains open: see Developement Remarks. | Implemented: credit notes API + UI (/rent/ioms/credit-notes) backed by /api/ioms/rent/credit-notes. What remains open: confirm SRS credit-note numbering/approval rules and accounting integration. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-005 | System shall provide invoice print functionality. | BR-RNT-005 | System shall support plain paper and pre-printed invoice formats. |  | SCR-RNT-02 | User | TC-M03-005 | Print invoice | Generate invoice → Print | Invoice printed in selected format | To be Checked | TDS logic for rent invoices is implemented, but GL posting is not. What remains open: see Developement Remarks. | Implemented: FY-based rent TDS calculation (Apr-Mar), tds fields on rent invoices + receipts, and PDF rendering. What remains open: GL posting rules for TDS and marginal-month behaviour if required. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-006 | System shall enforce approval workflow for invoice generation. | BR-RNT-006 | Invoice must pass DO, DV, and DA approval stages. | E-RNT-004 | SCR-RNT-01 | DO/DV/DA | TC-M03-006 | Submit invoice for approval | Generate → Submit → Approve | Invoice approved through workflow | To be Checked | Rent deposit ledger is implemented. What remains open: see Developement Remarks. | Implemented: rent deposit ledger API (/api/ioms/rent/ledger) and UI (/rent/ioms/ledger); GET /api/ioms/rent/ledger/trader-receipts lists IOMS receipts with payer TraderLicence for the same TA/tenant filter (supplemental panel on ledger screen). Receipts marked Paid can post Collection entries via hook. What remains open: GL posting bridge if finance mandates posted consolidation beyond deposit + receipt views. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-007 | System shall prevent duplicate invoice generation. | BR-RNT-007 | Duplicate invoices for same premises and period are not allowed. | E-RNT-005 | SCR-RNT-01 | DO | TC-M03-007 | Generate duplicate invoice | Generate invoice twice | System blocks duplicate | To be Checked | Dishonour/arrears disclosure exists but needs accounting closure. What remains open: see Developement Remarks. | Implemented: arrears disclosure on GET receipt + PDF after prior dishonour for same invoice; IOMS receipt detail page surfaces disclosure with invoice + ledger links; Outstanding dues rent pay dialog includes dishonour/arrears note and invoice link; PATCH Reversed can return rentDishonourScaffold with voucherCreateHref; VoucherCreate prefills from query string when finance records bank charge. What remains open: interest posting to GL and one-click posted bank charge if finance mandates. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-008 | System shall validate mandatory fields before invoice generation. | BR-RNT-008 | All required fields must be filled before submission. | E-RNT-006 | SCR-RNT-01 | DO | TC-M03-008 | Submit incomplete invoice | Leave fields blank → Submit | System shows validation errors | To be Checked | Rent invoice report/export features exist partially (reports + exports in repo). What remains open: see Developement Remarks. | Implemented: rent reports page + server-side report endpoints (see /rent/reports and routes-reports.ts). What remains open: confirm exact SRS report formats and any statutory exports beyond current implementation. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-009 | System shall log invoice transactions for audit. | BR-RNT-009 | All invoice actions must be recorded in audit logs. |  | SCR-RNT-01 | System | TC-M03-009 | Audit logging | Generate/cancel invoice | System records audit log | To be Checked | Monthly auto-generation for rent invoices exists. What remains open: see Developement Remarks. | Implemented: cron-based monthly Draft invoice generation for active allotments. What remains open: any SRS rule variations for proration, rent revision types, and audit/notifications. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-03 | FR-RNT-010 | System shall integrate invoice data with receipt module. | BR-RNT-010 | Invoice must be linked to receipt generation process. |  | SCR-RNT-01 | System | TC-M03-010 | Invoice to receipt linkage | Generate invoice → Create receipt | System links invoice and receipt | To be Checked | Rent revision configuration is now implemented minimally via overrides. What remains open: see Developement Remarks. | Implemented: rent_revision_overrides + UI/API; DO→DV→DA; cron/manual invoice use Approved overrides; revision_basis (FixedMonthlyRent ¦ OtherDocumented) on rows (015) for SRS classification — billing still uses approved rent_amount INR until percent/area auto-rules. What remains open: automated rule engine and ledger impacts on issued invoices if finance mandates. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-001 | System shall calculate market fee based on commodity transactions. | BR-MKT-001 | Market fee shall be calculated based on predefined commodity rate matrix. | E-MKT-001 | SCR-MKT-01 | DO | TC-M04-001 | Calculate market fee | Enter commodity details → Submit | System calculates fee correctly as per rate matrix | To be Checked | Earlier implementation used a free-form market fee % on purchase create. What remains open: see Developement Remarks. | Implemented: resolveMarketFeePercentForPurchase (yard-specific market_fee_rates row, else global yard_id NULL, else system_config market_fee_percent); GET /api/ioms/market/fee-preview; POST enforces match when client sends marketFeePercent and validates marketFeeAmount vs declared × resolved %. MarketTransactions UI loads preview read-only. What remains open: see this cell (pending items described above). | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-002 | System shall validate trader eligibility before transaction. | BR-MKT-002 | Only valid and active traders can perform transactions. | E-MKT-002 | SCR-MKT-01 | DO | TC-M04-002 | Invalid trader transaction | Select inactive trader → Submit | System blocks transaction | To be Checked | Purchase create did not enforce active / unblocked / in-validity trader licence. What remains open: see Developement Remarks. | Implemented: POST /api/ioms/market/transactions requires licence status Active, not is_blocked, and transactionDate within validFrom/validTo when both are ISO dates on the licence. What remains open: see this cell (pending items described above). | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-003 | System shall capture commodity details for transactions. | BR-MKT-003 | Commodity must be selected from predefined master list. | E-MKT-003 | SCR-MKT-01 | DO | TC-M04-003 | Invalid commodity | Enter invalid commodity → Submit | System restricts selection | To be Checked | Commodity must reference commodities master. What remains open: see Developement Remarks. | Implemented: POST still rejects unknown commodityId (404 PURCHASE_TX_COMMODITY_NOT_FOUND); fee matrix keyed by commodityId. What remains open: optional isActive filter on commodity if SRS requires inactive commodities blocked. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-004 | System shall apply fee exemptions where applicable. | BR-MKT-004 | Fee exemptions shall be applied for exempt categories as per rules. | E-MKT-004 | SCR-MKT-01 | System | TC-M04-004 | Fee exemption check | Select exempt category → Submit | System does not apply fee | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-005 | System shall maintain transaction records. | BR-MKT-005 | All transactions must be logged for audit purposes. |  | SCR-MKT-01 | System | TC-M04-005 | Transaction logging | Perform transaction | System records transaction in logs | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-006 | System shall generate daily transaction summaries. | BR-MKT-006 | System shall aggregate transactions into daily reports. |  | SCR-MKT-02 | System | TC-M04-006 | Daily summary generation | Run daily report | System generates accurate summary | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-007 | System shall enforce workflow approvals. | BR-MKT-007 | Transactions must pass DO, DV, and DA approval stages. | E-MKT-005 | SCR-MKT-01 | DO/DV/DA | TC-M04-007 | Transaction approval flow | Submit → Verify → Approve | System enforces workflow correctly | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-008 | System shall prevent duplicate transaction entries. | BR-MKT-008 | Duplicate entries for same trader and commodity are not allowed. | E-MKT-006 | SCR-MKT-01 | DO | TC-M04-008 | Duplicate transaction | Enter same transaction twice | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-009 | System shall validate mandatory fields before submission. | BR-MKT-009 | All required fields must be completed before submission. | E-MKT-007 | SCR-MKT-01 | DO | TC-M04-009 | Incomplete submission | Leave fields blank → Submit | System shows validation errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-04 | FR-MKT-010 | System shall integrate with receipt module. | BR-MKT-010 | Market fee transactions must link to receipt generation. |  | SCR-MKT-01 | System | TC-M04-010 | Transaction to receipt linkage | Complete transaction → Generate receipt | System links transaction to receipt | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-001 | System shall generate receipts for payments received against invoices. | BR-RCP-001 | Receipt must be generated only against valid and active invoice. | E-RCP-001 | SCR-RCP-01 | DO | TC-M05-001 | Generate receipt for invoice | Select valid invoice → Receive payment → Submit | Receipt generated successfully | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-002 | System shall validate payment amount before receipt generation. | BR-RCP-002 | Payment amount must not exceed outstanding invoice amount. | E-RCP-002 | SCR-RCP-01 | DO | TC-M05-002 | Overpayment attempt | Enter amount > due → Submit | System blocks transaction | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-003 | System shall support multiple payment modes. | BR-RCP-003 | Payment mode must be selected from predefined list (Cash, Cheque, Online). | E-RCP-003 | SCR-RCP-01 | DO | TC-M05-003 | Invalid payment mode | Enter invalid mode → Submit | System restricts selection | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-004 | System shall allow receipt cancellation. | BR-RCP-004 | Cancelled receipts must be marked and cannot be reused. | E-RCP-004 | SCR-RCP-01 | DO | TC-M05-004 | Cancel receipt | Cancel receipt → Save | System marks receipt as cancelled | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-005 | System shall generate receipt numbers automatically. | BR-RCP-005 | Receipt number must be unique and system-generated. |  | SCR-RCP-01 | System | TC-M05-005 | Receipt number generation | Generate receipt | System assigns unique receipt number | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-006 | System shall maintain receipt transaction logs. | BR-RCP-006 | All receipt transactions must be recorded for audit. |  | SCR-RCP-01 | System | TC-M05-006 | Audit log check | Generate/cancel receipt | System logs all actions | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-007 | System shall enforce approval workflow. | BR-RCP-007 | Receipts must pass DO, DV, and DA approval stages. | E-RCP-005 | SCR-RCP-01 | DO/DV/DA | TC-M05-007 | Receipt approval flow | Submit → Verify → Approve | System enforces workflow | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-008 | System shall prevent duplicate receipt entries. | BR-RCP-008 | Duplicate receipt for same invoice and payment not allowed. | E-RCP-006 | SCR-RCP-01 | DO | TC-M05-008 | Duplicate receipt | Generate same receipt twice | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-009 | System shall validate mandatory fields. | BR-RCP-009 | All required fields must be completed before submission. | E-RCP-007 | SCR-RCP-01 | DO | TC-M05-009 | Incomplete submission | Leave fields blank → Submit | System shows errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-05 | FR-RCP-010 | System shall integrate receipts with accounting/ledger module. | BR-RCP-010 | Receipt entries must update ledger records. |  | SCR-RCP-01 | System | TC-M05-010 | Ledger integration | Generate receipt | System updates ledger | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-001 | System shall generate payment vouchers for approved claims and payments. | BR-VCH-001 | Voucher must be generated only for approved claims or transactions. | E-VCH-001 | SCR-VCH-01 | DO | TC-M06-001 | Generate voucher without approval | Attempt voucher generation before approval | System blocks voucher generation | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-002 | System shall validate TA/DA claims before voucher generation. | BR-VCH-002 | TA/DA claims must comply with eligibility rules and limits. | E-VCH-002 | SCR-VCH-01 | DO | TC-M06-002 | Invalid TA/DA claim | Enter claim exceeding limit → Submit | System blocks claim | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-003 | System shall calculate payable amounts for vouchers. | BR-VCH-003 | Voucher amount must equal approved claim amount. |  | SCR-VCH-01 | System | TC-M06-003 | Voucher amount mismatch | Generate voucher | System calculates correct amount | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-004 | System shall enforce approval workflow for vouchers. | BR-VCH-004 | Voucher must pass DO, DV, and DA approval stages. | E-VCH-003 | SCR-VCH-01 | DO/DV/DA | TC-M06-004 | Voucher approval flow | Submit → Verify → Approve | System enforces workflow | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-005 | System shall assign unique voucher numbers. | BR-VCH-005 | Voucher number must be unique and system-generated. |  | SCR-VCH-01 | System | TC-M06-005 | Voucher numbering | Generate voucher | System assigns unique number | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-006 | System shall support voucher cancellation. | BR-VCH-006 | Cancelled vouchers must be marked and cannot be reused. | E-VCH-004 | SCR-VCH-01 | DO | TC-M06-006 | Cancel voucher | Cancel voucher → Save | System marks voucher as cancelled | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-007 | System shall maintain audit logs for vouchers. | BR-VCH-007 | All voucher actions must be recorded in audit logs. |  | SCR-VCH-01 | System | TC-M06-007 | Audit logging | Generate/cancel voucher | System logs actions | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-008 | System shall prevent duplicate vouchers. | BR-VCH-008 | Duplicate voucher for same transaction is not allowed. | E-VCH-005 | SCR-VCH-01 | DO | TC-M06-008 | Duplicate voucher | Generate voucher twice | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-009 | System shall validate mandatory fields. | BR-VCH-009 | All required fields must be completed before submission. | E-VCH-006 | SCR-VCH-01 | DO | TC-M06-009 | Incomplete submission | Leave fields blank → Submit | System shows validation errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-06 | FR-VCH-010 | System shall integrate vouchers with accounting system. | BR-VCH-010 | Voucher entries must update accounting/ledger records. |  | SCR-VCH-01 | System | TC-M06-010 | Ledger integration | Generate voucher | System updates ledger | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-001 | System shall maintain vehicle master records. | BR-VEH-001 | Each vehicle must have a unique registration number. | E-VEH-001 | SCR-VEH-01 | DO | TC-M07-001 | Register duplicate vehicle | Enter same vehicle number → Submit | System blocks duplicate vehicle registration | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-002 | System shall allow assignment of vehicles to trips. | BR-VEH-002 | Vehicle must be available and not assigned to another active trip. | E-VEH-002 | SCR-VEH-01 | DO | TC-M07-002 | Assign busy vehicle | Assign vehicle already in use | System blocks assignment | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-003 | System shall track fuel usage for vehicles. | BR-VEH-003 | Fuel consumption must be recorded for each trip. |  | SCR-VEH-02 | DO | TC-M07-003 | Track fuel usage | Enter trip details → Save | System records fuel usage | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-004 | System shall maintain maintenance records. | BR-VEH-004 | Vehicle maintenance history must be recorded and retrievable. |  | SCR-VEH-03 | DO | TC-M07-004 | Record maintenance | Enter maintenance details → Save | System stores maintenance history | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-005 | System shall validate vehicle availability. | BR-VEH-005 | Vehicle must be marked active and available for assignment. | E-VEH-003 | SCR-VEH-01 | DO | TC-M07-005 | Assign inactive vehicle | Select inactive vehicle → Assign | System blocks assignment | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-006 | System shall enforce workflow approvals. | BR-VEH-006 | Vehicle operations must pass DO, DV, and DA approval stages. | E-VEH-004 | SCR-VEH-01 | DO/DV/DA | TC-M07-006 | Approval workflow | Submit → Verify → Approve | System enforces approval flow | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-007 | System shall prevent duplicate entries. | BR-VEH-007 | Duplicate vehicle or trip records are not allowed. | E-VEH-005 | SCR-VEH-01 | DO | TC-M07-007 | Duplicate record | Enter duplicate record | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-008 | System shall validate mandatory fields. | BR-VEH-008 | All required fields must be completed before submission. | E-VEH-006 | SCR-VEH-01 | DO | TC-M07-008 | Incomplete submission | Leave fields blank → Submit | System shows validation errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-009 | System shall maintain audit logs. | BR-VEH-009 | All vehicle-related actions must be logged for audit. |  | SCR-VEH-01 | System | TC-M07-009 | Audit log check | Perform actions | System logs all activities | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-07 | FR-VEH-010 | System shall generate vehicle reports. | BR-VEH-010 | System shall generate reports for vehicle usage and maintenance. |  | SCR-VEH-04 | System | TC-M07-010 | Generate report | Run report | System generates accurate reports | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-001 | System shall create and manage work orders for construction and maintenance. | BR-WRK-001 | Each work order must have a unique identifier and cannot be duplicated. | E-WRK-001 | SCR-WRK-01 | DO | TC-M08-001 | Create duplicate work order | Enter same work details → Submit | System blocks duplicate work order | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-002 | System shall allow assignment of contractors to work orders. | BR-WRK-002 | Contractor must be valid and registered in the system. | E-WRK-002 | SCR-WRK-01 | DO | TC-M08-002 | Assign invalid contractor | Select unregistered contractor → Submit | System blocks assignment | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-003 | System shall track progress of work orders. | BR-WRK-003 | Work progress must be updated at defined stages. |  | SCR-WRK-02 | DO | TC-M08-003 | Update work progress | Update progress → Save | System records progress correctly | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-004 | System shall validate cost estimates for work orders. | BR-WRK-004 | Work cost must be within approved budget limits. | E-WRK-003 | SCR-WRK-01 | DO | TC-M08-004 | Exceed budget | Enter cost > budget → Submit | System blocks submission | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-005 | System shall support work completion tracking. | BR-WRK-005 | Work order must be marked complete only after verification. | E-WRK-004 | SCR-WRK-01 | DO/DV | TC-M08-005 | Mark incomplete work as complete | Mark complete without verification | System blocks completion | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-006 | System shall enforce approval workflow. | BR-WRK-006 | Work orders must pass DO, DV, and DA approval stages. | E-WRK-005 | SCR-WRK-01 | DO/DV/DA | TC-M08-006 | Approval workflow | Submit → Verify → Approve | System enforces workflow | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-007 | System shall maintain audit logs for work orders. | BR-WRK-007 | All work-related actions must be recorded for audit. |  | SCR-WRK-01 | System | TC-M08-007 | Audit logging | Perform actions | System logs all activities | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-008 | System shall prevent duplicate work entries. | BR-WRK-008 | Duplicate work orders for same task are not allowed. | E-WRK-006 | SCR-WRK-01 | DO | TC-M08-008 | Duplicate work entry | Enter duplicate work → Submit | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-009 | System shall validate mandatory fields. | BR-WRK-009 | All required fields must be filled before submission. | E-WRK-007 | SCR-WRK-01 | DO | TC-M08-009 | Incomplete submission | Leave fields blank → Submit | System shows validation errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-08 | FR-WRK-010 | System shall generate reports for work orders. | BR-WRK-010 | System shall generate reports for work progress and cost. |  | SCR-WRK-03 | System | TC-M08-010 | Generate report | Run report | System generates accurate reports | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-001 | System shall register inward correspondence (Tapal). | BR-COR-001 | Each inward tapal must have a unique reference number. | E-COR-001 | SCR-COR-01 | DO | TC-M09-001 | Register duplicate tapal | Enter same tapal no → Submit | System blocks duplicate entry | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-002 | System shall dispatch outward correspondence. | BR-COR-002 | Outward correspondence must be linked to valid inward reference where applicable. | E-COR-002 | SCR-COR-01 | DO | TC-M09-002 | Dispatch without reference | Submit without reference | System blocks dispatch | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-003 | System shall track correspondence status. | BR-COR-003 | Status must be updated at each stage (Received, Under Process, Dispatched). |  | SCR-COR-01 | DO | TC-M09-003 | Update status | Change status → Save | System updates status correctly | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-004 | System shall prevent duplicate correspondence entries. | BR-COR-004 | Duplicate tapal numbers are not allowed. | E-COR-003 | SCR-COR-01 | DO | TC-M09-004 | Duplicate entry | Enter same tapal twice | System blocks duplicate | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-005 | System shall validate mandatory fields. | BR-COR-005 | All required fields must be filled before submission. | E-COR-004 | SCR-COR-01 | DO | TC-M09-005 | Incomplete submission | Leave fields blank | System shows validation errors | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-006 | System shall maintain audit logs for correspondence. | BR-COR-006 | All correspondence actions must be recorded in audit logs. |  | SCR-COR-01 | System | TC-M09-006 | Audit log check | Perform actions | System logs all activities | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-007 | System shall enforce workflow approvals. | BR-COR-007 | Correspondence must pass DO, DV, and DA approval stages. | E-COR-005 | SCR-COR-01 | DO/DV/DA | TC-M09-007 | Approval workflow | Submit → Verify → Approve | System enforces workflow | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-008 | System shall allow document attachment. | BR-COR-008 | Documents must be attached in supported formats only. | E-COR-006 | SCR-COR-02 | DO | TC-M09-008 | Invalid file format | Upload unsupported file | System rejects upload | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-009 | System shall generate correspondence reports. | BR-COR-009 | Reports must include inward and outward correspondence details. |  | SCR-COR-03 | System | TC-M09-009 | Generate report | Run report | System generates accurate report | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-09 | FR-COR-010 | System shall maintain document movement history. | BR-COR-010 | Movement history must be traceable for each correspondence. |  | SCR-COR-01 | System | TC-M09-010 | Track movement | View history | System displays full movement trail | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-10 | FR-USR-001 | System shall create user accounts mapped to employees. | BR-USR-001 | User must be linked to a valid employee record. | E-USR-001 | SCR-USR-01 | Admin | TC-M10-001 | Create user without employee | Attempt creation | System blocks creation | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-002 | System shall assign roles to users. | BR-USR-002 | User must have at least one role assigned. | E-USR-002 | SCR-USR-01 | Admin | TC-M10-002 | Create user without role | Submit without role | System blocks submission | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-003 | System shall enforce role-based access. | BR-USR-003 | Access to modules must be restricted based on assigned roles. | E-USR-003 | SCR-USR-01 | System | TC-M10-003 | Unauthorized access | Login as limited user | System restricts access | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-004 | System shall support user activation/deactivation. | BR-USR-004 | Inactive users must not be allowed to login. | E-USR-004 | SCR-USR-01 | Admin | TC-M10-004 | Login with inactive user | Attempt login | System blocks access | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-005 | System shall enforce password security. | BR-USR-005 | Password must meet complexity requirements. | E-USR-005 | SCR-USR-02 | User | TC-M10-005 | Weak password | Enter weak password | System rejects password | To be Checked | Local password policy was weaker than BR-USR-10 (min 8). What remains open: see Developement Remarks. | Implemented: shared/password-policy-br-usr-10.ts + assertPasswordComplexityBrUsr10 on POST/PUT employee login; HR UI hints updated; seed passwords updated to compliant defaults (GapmcAdmin@2026!, GapmcUsers@2026!). What remains open: see this cell (pending items described above). | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-10 | FR-USR-006 | System shall maintain session control. | BR-USR-006 | User sessions must expire after inactivity. |  | SCR-USR-02 | System | TC-M10-006 | Session timeout | Stay idle | System logs out user | To be Checked | Gap: checklist item not yet verified in this repo. What remains open: see Developement Remarks. | What remains open: verify implementation against SRS and update RESULT accordingly. | Partial — engineering delivered; UAT / CA / finance confirmation still needed
M-10 | FR-USR-007 | System shall prevent duplicate users. | BR-USR-007 | Duplicate user IDs are not allowed. | E-USR-006 | SCR-USR-01 | Admin | TC-M10-007 | Duplicate user | Create same user | System blocks duplicate | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-008 | System shall validate mandatory fields. | BR-USR-008 | All required fields must be filled before submission. | E-USR-007 | SCR-USR-01 | Admin | TC-M10-008 | Incomplete form | Submit blank fields | System shows validation errors | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-009 | System shall maintain audit logs. | BR-USR-009 | All user actions must be logged for audit. |  | SCR-USR-01 | System | TC-M10-009 | Audit log check | Perform actions | System logs activity | Implemented |  |  | Development complete — behaviour present in repo for this FR
M-10 | FR-USR-010 | System shall support role-permission mapping. | BR-USR-010 | Roles must be mapped to specific permissions. |  | SCR-USR-03 | Admin | TC-M10-010 | Assign permissions | Assign role | System enforces permissions | Implemented | Menu ( Form Level Assignment is required. |  | Development complete — behaviour present in repo for this FR